## Slide 1: Certification Lessons Learned
Entity Insights From Regional Certifications
July 2025

## Slide 2: Today’s Discussion
Review of Lessons Learned
Preparations
for a Certification

## Slide 3: Review of Lessons Learned
Themes within Certifications
  EMS Vendors
    Ensure the vendor understands the scope of the project
    Ensure the vendor has enough support; they may be providing support for other entities
    If a complete change-out from a legacy EMS is required, make sure the vendor understands the need to provide operators with appropriate training under contractual agreements
Example risks with the vendor during the EMS process, but were mitigated by the Entity
  Poor Database and display conversions​
  Delayed delivery of a functioning AGC module ​
  System delivery was not complete​
  Slow to address defects​
  Synchronization of environments was challenging​
  Documentation lacks clarity and applicability​
  Promised features that were difficult or could not be implemented​

## Slide 4: Review of Lessons Learned
Themes within Certifications
  EMS Vendors
    Ensure the vendor understands the specific data that needs to be tested, and if they can do the testing with the entity data
  Documentation
    Ensure all documentation is finalized
    Ensure counterparty agreements (RC, GOP, TOP) are finalized at the time of certification documentation submission.
    Develop Internal Controls Documentation to cover both O&P and CIP to support an effective review during the Certificaiton

## Slide 5: Review of Lessons Learned (Cont.)
Themes within Certifications
  Control Centers
    Control Center Construction Companies
    New PSP and ESP meeting CIP requirements that the entity might not have realized
    Need to understand that all approvals for construction are up to date (Certification of Occupancy COO)
  Backup Control Center
    Order of operations is essential post-move. Interdependencies between equipment and systems may rely on sequence and the order in which systems are brought online
    Always consider potential supply chain risks for critical items in the event of a severe impact (e.g., Covid)

## Slide 6: Preparations for A Certification
Entities should engage the Regional Entity early
Engage with your Regional Entity for questions that come up during a Certification, Certification Review, and Lesser Activity engagement
Ensure the project implements all necessary regulatory steps, milestones for compliance, such as:
  Document updates
  Revised evidence
  ERO engagement for certification